EXAMPLE:  Commonly overlooked rules

Table 1: Summary of Results framework

| UNDAF Outcome 2: By 2010, livelihoods and food security among most vulnerable groups are improved in highly affected locations |
| --- |
| Joint Programme Outcome 3: Food security and incomes for women, youth and other vulnerable groups are sustainably improved. |
| Indicators: 3.1 Proportion of households living in relative poverty and extreme poverty (MDG1); Baseline 2003/4: 35 % ; Target 2012 41% |
| 3.2 Yield of subsistence crops Kg per hectare e.g. Caprivi maize Baseline (2003/4): 600 , Target 2010: 790. |
| 3.3 # of animals which are marketed in northern communal areas e.g. cattle. Baseline (2003/4) 17.776 ; Target 2010: CBS-NPC, Annual Agricultural Survey |
| JP Outputs (Give corresponding indicators and baselines) | SMART Outputs and Responsible UN Organization | Reference to Agency priority or Country Programme | Implementing Partner | Indicative activities for each Output | Resource allocation and indicative time frame* |
|  |  |  |  |  | Y1 | Y2 | Y3 | TOTAL |
| 3.1 Food availability, access and utilization improved through appropriate farming systems Indicators: Yield of subsistence crops Kg per hectare Baseline (2003/4): 600 , Target 2010: 790. # of animals which are marketed in northern communal areas e.g. cattle | 15 Junior farm schools reach 450 youth (150 boys and girls, each) by 2010 | UNICEF | MOE | 1. Establish and scale up Junior Farmer Field and life skills in-school curriculum in targeted areas, for vulnerable children | 1000 | 4000 | 500 | 5500 |
|  | 15 Senior farm schools reach 450 households (disaggr.) by 2010 | FAO | MAWF | 2. Establish Senior (above 18 yrs) Farmers Field and Life Skills ‘schools’ in conservation agriculture, based on needs assessments, including female headed households & SAN, PLWHA & TB support groups, with a range of agricultural inputs. (Baseline 86% women) | 300 | 4000 | 9000 | 13300 |
|  | 300 households engaged in improved agric. Practices by 2010 | FAO | MAWF | 4. Support agricultural practices in peri and urban communities e.g micro gardening | 1000 | 2000 | 9700 | 12700 |
|  | 300 households taking up new technology by 2010 | UNICEF | MOH | 5. Conduct training on small scale appropriate technologies to improve nutrition | 700 | 400 | 5000 | 6000 |
|  | 150 households benefiting from aquaculture by 2010 | UNDP | MFMR | 6. Provide support to community aquaculture activities |  |  |  |  |

# EXAMPLE of Annex A: Common Work plan and Budget

| Annual Targets | Key Activities | Timeframe | UN Agency | Responsible Party | Planned Budget |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007 |  |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Total Amount |
| Output 1 Improved knowledge and skills of officials and technical staff of the line ministries, district community authorities in Yerevan, 10 governor offices and 100 communities in the regions of Armenia to integrate HIV/AIDS activities into community development plans and to implement the activities that are rights-based, participatory, and promote access to HIV/AIDS information and services Target: -By October 2005, 520 national, regional and local Government officials and technical staff will have passed training and skills building courses 95% of course participants will have indicated substantial improvement in their knowledge and skills in the areas covered by the courses (based on the pre- and post evaluation of the participants) | Development and printing of a training manual |  |  |  |  | UNAIDS | ANAF | MGD-F | 1.1Supplies/ commodities/ equipment/transport 1.2 Personnel 1.3 Training of counterparts 1.4Contracts 1.5 Other Direct Costs 2.0 UN Agency Indirect Cost | 20,000 60,000 40,000 50,000 5,000 12,250 |
|  | Identification of the government officials at the national regional and community levels in Yerevan and the regions of Armenia who are eligible for the knowledge and skills building training courses |  |  |  |  | UNFPA | MOH | MGD-F | 1.1 Supplies/ commodities/ equipment/transport 1.2 Personnel 1.3 Training of counterparts 1.4Contracts 1.5 Other Direct Costs 2.0 UN Agency Indirect Cost | 5,000 20,000 10,000 10,000 2,000 3,290 |

# Text boxes

4.  Be sure to insert a column for TOTAL

2.  It is important that only ONE Agency be listed next to each output. It is essential to ensure accountability.  Reference to the UN agency’s country programme or priority should be listed here

1.  These OUTPUTS should be SMART  (Specific, Measurable, Achievable, Realistic and Time related) and would be a sub-set of the JP outputs in the previous column.

3.  As in previous column only ONE Implementing Partner should be in each line.

List only ONE UN- Agency. If responsible Party is not yet known, can list TBA

List actual Activities, NOT budget descriptions